## General graphic
Sprint | Pass | Fail | Pending | N/A
Sprint 1 | 0 | 0 | 6 | 0

## Sprint 1
S. No | Subject | Test Name | Description | Step Name (Design Steps) | Description (Design Steps) | Preconditions | Expected Result (Design Steps) | Execution Type | Priority | Status | Complexity | Type | Regression candidate priority | Result | Issue observed along with date | Retest Date | Retesting done? | Status | Comments
1 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | UC01_M_TC01_PC1_DP_Entity Selection | Validating entity selection mashup through left Slider | Step 1 | Select 'Papa' Department from the drop down list. | Be logged in the platform, then click on the Hamburger menu icon displayed on the left side of the screen and click on 'Department' drop down list. | Should able to see all the available Lines, Areas(PC1Packaging, PC1Processing, PC1 and Zones/Units that belongs to the selected department. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pending
2 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | UC01_M_TC02_PC1_DP_Entity Selection | Validating entity selection mashup through left Slider | Step 2 | Click on 'PC1Packaging' area. | Have selected the 'Papa' department. | Slider should be closed and load the dashboard with details of the selected entity. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pending
3 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | UC02_M_TC01_PC1_DP_Overview tab | Validating Overview tab | Step 1 | Click on 'Downtime' tab | Have selected the 'PC1Packaging' area. | The DownTime Overview tab will be opened showing all the downtimes and their information. | [6 empty] | Pending
4 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | UC03_M_TC01_PC1_DP_Cronologhical events | Validating Cronologhical events tab | Step 1 | Click on 'Cronologhical events' button | Be in the Downtime tab. | The Cronologhical events tab will be opened showing all the events. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pending
5 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | UC04_M_TC01_PC1_DP_Downtime times | Validating Downtime times | Step 1 | Clear all the filters selected | Be in the Cronologhical events tab. | The information displayed on the dashboard must contain all data. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pending
6 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | UC04_M_TC02_PC1_DP_Downtime times | Validating Downtime times | Step 2 | Observe the Downtimes that are open | All filters have been removed. | The time shown for each open Downtime must be less than 8 hours. | [6 empty] | Pending
Pass
Pending
Fail
N/A