## Hoja1
S. No | Subject | Test Name | Description | Step Name (Design Steps) | Description (Design Steps) | Expected Result (Design Steps) | Execution Type | Priority | Status | Complexity | Type | Regression candidate priority | Result | Issue observed along with date | Retest Date | Retesting done? | Status | Comments
1 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC01_M_PC65_DP_Access TWX dashboard | Access TWX dashboard | Step 1 | https://meswebgsft.azure.intra.pepsico.com/Thingworx/Runtime/index.html#master=PepsiCo_Master&mashup=MES_Dashboard | Should be able to prompt for an authentication window for login. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
2 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC01_M_PC01_DP_Access TWX dashboard | Access TWX dashboard through credentials | Step 2 | Enter user's credential to view ThingWorx dashboard home page | Should allow user to view ThingWorx dashboard | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
3 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC02_M_PC01_DP_Entity Selection left slider | Validating entity selection mashup through left Slider | Step 1 | Click on the Hamburger menu icon displayed on the left side of the screen. | User should see a slider displaying Department dropdown, Lines, Areas and Zones/Units. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
4 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC02_M_PC02_DP_Entity Selection left slider | Validating entity selection mashup through left Slider | Step 2 | Click on 'Department' drop down list. | Should list all the applicable Departments. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
5 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC02_M_PC03_DP_Entity Selection left slider (same name back) | Validating entity selection mashup through left Slider | Step 3 | Select 'Papa' Department from the drop down list. | Should able to see all the available Lines, Areas(PC65Packaging, PC65Processing, PC65 and Zones/Units that belongs to the selected department. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
6 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC02_M_PC04_DP_Entity Selection left slider | Validating entity selection mashup through left Slider | Step 4 | Click on 'PC65Packaging' area.(pc65)¿? | Slider should be closed and load the dashboard with details of the selected entity. | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
| Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC03_M_PC01_DP_Efficiency, Capacity, Waste and Downtime values | Validate values of Efficiency, Capacity, Waste and Downtime indicators | Step 1 | Click on 'Overview' tab | All the packaging tubes must be displayed with their Efficiency, Capacity, Waste and Downtime values. | [6 empty] | Pass
7 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC03_M_PC02_DP_Efficiency, Capacity, Waste and Downtime values | Validate values of Efficiency, Capacity, Waste and Downtime indicators | Step 2 | Observe the Efficiency, Capacity and Waste value | The value displayed on the dashboard must be >0 WASTE(<10) | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass
8 | Release\SIT\PC1PKG09\Efficiency Dashboard\01.gSFT Packaging Area and Tube | TC03_M_PC03_DP_Efficiency, Capacity, Waste and Downtime values | Validate values of Efficiency, Capacity, Waste and Downtime indicators | Step 3 | Observe the Downtime value | The value displayed on the dashboard must be <100 | 1-Manual | 1-Critical | 1-New | 1-Simple | MANUAL | Non-Candidate | Pass